## Sheet1
Week | Dates | Tasks | Description
1 | September 24 - October 1 | Initial Project Plan | Met on 9/27/2019. Discussed roles and responsibilities. Created this schedule, a commnication plan, and an initial work breakdown.
2 | October 2 - October 8 | Requirements Document | Going to meet after class is held to create the requirements document.
3 | October 9 - October 15 | Final Project Plan | Will meet to revise initial plan and to state the requirements of the project. Here the project schedule will be revised with the status of tasks.
4 | October 16 - October 22 | Software Development | Time to continue working on tasks.
5 | October 23 - October 29 | Continued Software Development & Presentation | We will record a 5-8 minute video to demonstrate the skill we created and explain the work we did.